## Project Management
REAL Change PROGRESS CHART FOR The Right Support in MY Home:
CODE
RED | Not Started
YELLOW | Underway
Green | Completed
PHASE | ACTIONS | Apr-16 | May-16 | Jun-16 | Jul-16 | Aug-16 | Sep-16 | Oct-16 | Nov-16 | Dec-16 | Jan-17 | Feb-17 | Mar-17 | Apr-17
PHASE 1: PLANNING
Team | Confirm Team Members
Orient Teams on Guidelines and Tools
Identify Specific Roles for Team Members (eg. Journal keeper, facilitator, leader etc.)
Pilot | Determine Pilot Title
Develop Purpose Statement
Other:
Detailed Description of the Pilot | Set Goals/ Intended Outcomes
SEE "KEY ACTION STEPS PAGE" | Break down action steps - see next SHEET
Identify Resources Needed
Set Timeframes
Identify Who is Responsible
Other:
Develop Evaluation | Identify Who Needs Results from Evaluation
Set Measures of Success
Set Measurable Indicators
Decide on Targets
Develop Evaluation Questions
Develop , Review and Finalize Evaluation Tools
Create the Digital Journal
Set Timeframes for Evaluation
Set budget and resources for evaluation
Finalize Pilot | Submit to RCSC
Make Revisions
Finalize Framework and Roadmap Document
PHASE 2: IMPLEMENTATION | (Implementation Steps will be developed and will be unique for each Pilot)
(TO BE FILLED IN AFTER PLANNING PHASE)
Record baseline information for measures
PHASE 3: EVALUATION | (TO BE FILLED IN AFTER PLANNING PHASE)
Set Dates for Pilot Meetings
PROJECT MANAGEMENT | Agenda for Meeting Written & Distributed
Digital Journal Updated
Notes from Meeting Disseminated
Meeting information Presented to RCSC
Follow-Up From Meeting Completed
Process Changes Identified
New Resources required Identified
Communication requirements forwarded to Comm. Ctee.

## Key Action Steps
KEY ACTION STEPS | Detailed Actions | Person Responsible | 2016-06-01 | 2016-07-01 | 2016-08-01 | 2016-09-01 | 2016-10-01 | 2016-11-01 | 2016-12-01 | 2017-01-01 | 2017-02-01 | 2017-03-01 | 2017-04-01
ASSESSMENT TOOL | Make a list of what the assessment tool needs to identify
Find potential tools that can be used
Review tools and select tools
Adapt assessment tools
Test tools to make sure they meet the needs
Finalize the tools
PEOPLE | Identify 30 people who may benefit from being part of the pilot
Identify 2 people from the initial list of 30, as the first group
Identify 2 TAY who will be part of the pilot
Create a list of the 'next people' who will come on board
FOR THE PILOT PARTICIPANTS | For the 4 pilot people, baseline current support requirements and affiliated costs
Cost out current supports for each person
Conduct the assessment
Review information from assessment and identify support needs for each person
Identify technology supports for each person
Finalize a plan for each person
Identify potential partners for providing supports and other services
Select partners
PLACES TO OFFER SUPPORT | Identify the types of places where services will be provided, from the assessment tool.
Identify places where service can potentially be provided
Secure places where services will be provided to the pilot participants
Decide on a move date
Prepare for the move
Move
TECHNOLOGY | Connect with a technology provider to conduct a technology assessment
Identify potential products that can enable independence
Review tech options against person's plan
Cost the tech. needed for the person to be successful
Decide on technology
Purchase technology
PARTNERS | Identify what potential needs partners can help meet
Develop a list of potential partners and the reciprocal relationships that are anticipated from each partnership
contact the potential partners and gauge interest
Select partners with the most mutual benefit
Connect with selected partners and secure support
Develop partnership agreements
Move forward with partnerships